 

**TOOMBS COUNTY**

**REQUEST FOR BID**

Seal Bids will be accepted on the following project (Project 2017-R&B-Var-001) until 12:00 Noon, June 23, 2017 and will be opened at the Public Bid opening to be held in the Commissioner's Office and will be recorded at that time. Seal Bids can be submitted to: County Manager, 100 Courthouse Square, PO Box 112, Lyons, GA. 30436. The Board of Commissioners reserves the right to accept or reject any and all bids. All bids shall include providing all labor, equipment, and materials or other things necessary to complete the project. Project will require a milling machine.

Various patching of approximately 40-45 patches of various widths and lengths on approximately 11 roads. Roads and patching requirements listed on Schedule A & B.

Mill and inlay 5 bridges for smooth transition for SO foot apron on each side of the bridge. Milling should be 2 inches below bridge deck. Bridges are located on:

Old Normantown Road - 2 Bridges Vidalia-Cedar Crossing road - 3 bridges

**Note: Contractor is responsible for all traffic control and the posting of appropriate construction signs as required by MUTCD**

The successful bidder will be GDOT Certified and submit certification of workers' comp., liability insurance and e-verify compliance when the bid is awarded.

**The Contractor shall be responsible for attending pre-construction conference after award of bid and completing the project within 60 days of Notice To Proceed for Schedule A and 120 days on Notice to Proceed for Schedule B.**

**PROJECT 2017-R-VAR-001**

SCHEDULE A

**AS** - **Scott Drive:**

**SCHEDULE A-Complete within 60 DAYS of Notice to Proceed**

**Al -McNatt Falls/Chambers Road:**

**SIZE (FT)**

**A2- Center Subdivision**

2 x 2 Clean out and 3" of asphalt

**A3** - **Pinewood Subdivision**

**A4** - **Marshall Pittman Road**

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| 34 McNatt Falls RD | 114 | x | 5 | 5" asphalt |
| N/A | 6 | X | 4 | 311 Mill & Inlay |
| 628 McNatt Falls RD | 9 | x | 4 | 3" Mill & Inlay |
| 762/763 McNatt Falls RD | 31 | x | 4 | 3" Mill & Inlay |
|  | 10 | x | 16 | 3" Mill & Inlay |
| By Guard Rail | 60 | x | 10 | Tear-out - 8" GAB & 4" of Asphalt |
|  |  |  |  | Removed dirt can be placed on  backside of rail on river side. |

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| Corner of Ridgewood Ct/Pinewood | 2 | x | 20 | 3" Mill & Inlay |
| Corner of Ridgewood CT/Pinecrest Ct. | 2 | x | 2 | 3" Mill & Inlay |
| Corner of Pinewood CT/Centerbrook Ct | 5 | x | 5 | 3" Mill & Inlay |
|  | 5 | x | 5 | 3" Mill & Inlay |

|  |  |  |  |
| --- | --- | --- | --- |
| 5 | X | 5 | 311 Mill & Inlay |
| 5 | X | 5 | 311 Mill & Inlay |
| 6 | x | 25 | 4" GAB & 2" of Asphalt |
| 10 | x | 90 | 6' GAB & 4' of Asphalt |
| 10 | x | 60 | 6' GAB & 4' of Asphalt |

PROJECT 2017-R-VAR-001 SCHEDULE A

|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| SCHEDULE B - Complete within 120Days of Notice to Complete  **SIZE (FT)** | | | | |
| **81** - C.**V. Mosley** | 2 | X | 5 | Patch |
|  | 144 | X | 22 | 1 1/ 211 Overlay |
|  | 40 | X | 11 | Patch |
|  | 128 | X | 22 | 4" GAB & 2" Asphalt |
|  |  |  |  | Pack Asphalt down centerline |
| **82** - **Dewayne Dykes Road** | 66 | X | 22 | 4" GAB & 2" of Asphalt |
| **83** - **Old Normantown Road:** |  |  |  |  |
|  | 14 | X | 22 | 3" Mill & Inlay |
|  | 78 | X | 11 | 3" Mill & Inlay |
|  | 15 | X | 11 | 3" Mill & Inlay |
|  | 20 | X | 11 | 3" Mill & Inlay |
|  | 10 | X | 12 | 3" Mill & Inlay |
|  | 4 | X | 2 | 3" Mill & Inlay |
|  | 4 | X | 13 | 3" Mill & Inlay |
|  | 360 | X | 11 | 3" Mill & Inlay |
|  | 48 | **X** | 22 | 311 Mill & Inlay |
|  | 46 | **X** | 11 | 311 Mill & Inlay |
|  | 100 | X | 11 | 311 Mill & Inlay |
|  | 76 | **X** | 11 | 3" Mill & Inlay |
|  | **20** | **X** | 11 | 3" Mill & Inlay |
|  | 101 | X | 11 | 3" Mill & Inlay |
|  | 20 | X | 11 | 3" Mill & Inlay |
| **BRIDGES:** |  |  |  |  |
| Old Normantown Road - 2 Bridges |  |  |  |  |
| Vidalia-Cedar Crossing Road - 3 bridges |  |  |  |  |